## RLE Cost Est
Description |  | Quantity | Cost (March 2024) | Cost (October 2024) | Change
10 GUIDWAY & TRACK ELEMENTS (5.45 ROUTE MILES)
10.01 | Guideway: At-grade exclusive right-of-way | 1.54 | 9247039.7508 | 49175031 | 431.8%
10.04 | Guideway: Aerial structure | 3.86 | 751377361.6759 | 442575283 | -41.1%
10.08 | Guideway: Retained cut or fill | 0.11 | 9244253.2389 | 30883659 | 234.1%
10.09 | Track: Direct fixation | 40761.6 | 64258357.7439 | 79067998 | 23.05%
10.11 | Track: Ballasted | 17424 | 28820892.6149 | 29439663 | 2.147%
10.12 | Track: Special (switches, turnouts) | 13 | 9326455.34 | 17690200 | 89.68%
10.13 | Track: Vibration and noise dampening |  | 0 | 6622055
Subtotal (10) |  |  | 872274360.3644 | 655453889 | -24.86%
20 STATIONS, STOPS, TERMINALS, INTERMODAL (4 STATIONS)
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 1 |  | 130653113
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 4 (then 3) | 197534435.5624 | 391959337 | 98.43%
20.06 | Automobile parking multi-story structure | 650 | 61202947.442 | 29999979 | -50.98%
20.07 | Elevators, escalators | 17 | 15054130.5571 | 29253236 | 94.32%
Subtotal (20) |  |  | 273791513.5615 | 581865665 | 112.5%
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN BLDGS.
30.02 | Light Maintenance Facility |  |  | 1643682
30.03 | Heavy Maintenance Facility | 120727 | 249015242.9741 | 160778986 | -35.43%
30.05 | Yard and Yard Track | 2265120 | 257044577.0232 | 150123622 | -41.6%
Subtotal (30) |  |  | 506059819.9974 | 312546290 | -38.24%
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork | 1 | 53505208.3094 | 129115507 | 141.3%
40.02 | Site Utilities, Utility Relocation | 1 | 32536706.2378 | 56776112 | 74.5%
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 1 | 52286109.3518 | 153336346 | 193.3%
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 1 | 22016230.5472 | 7433359 | -66.24%
- | Site structures including retaining walls, sound walls | 1 | 24483686.8375 | 0 | -100%
40.06 | Pedestrian / bike access and accommodation, landscaping | 1 | 20813850.661 | 11578559 | -44.37%
40.07 | Automobile, bus, van accessways including roads, parking lots | 1 | 22055241.7139 | 63999555 | 190.2%
40.08 | Temporary Facilities and other indirect costs during construction | 1 | 65687838.3502 | 145580014 | 121.6%
Subtotal (40) |  |  | 293384872.0089 | 567819452 | 93.54%
50 SYSTEMS
50.01 | Train control and signals | 5.51 | 363868830.8798 | 330313299 | -9.222%
50.02 | Traffic signals and crossing protection | 20 | 15740540.6293 | 9006883 | -42.78%
50.03 | Traction power supply: substations | 6 | 301602939.1239 | 224172552 | -25.67%
50.04 | Traction power distribution: catenary and third rail | 5.51 | 96568925.7939 | 130358177 | 34.99%
50.05 | Communications | 5.51 | 33793948.0843 | 23527187 | -30.38%
50.06 | Fare collection system and equipment | 1 | 10018641.4005 | 17008624 | 69.77%
50.07 | Central Control | 1 | 16416958.4563 | 4078669 | -75.16%
Subtotal (50) |  |  | 838010784.3679 | 738465391 | -11.88%
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate | 1 | 164156418.8224 | 103038708 | -37.23%
60.02 | Relocation of existing households and businesses | 1 | 10258662.2115 | 12980449 | 26.53%
Subtotal (60) |  |  | 174415081.0339 | 116019157 | -33.48%
70 VEHICLES (78 CARS)
70.02 | Heavy Rail | 78 | 410823902.0017 | 306560352 | -25.38%
70.07 | Spare Parts | 1 |  | 16134755
Subtotal (70) |  |  | 410823902.0017 | 322695107 | -21.45%
80 PROFESSIONAL SERVICES (applies to cats. 10-50)
| Preliminary Engineering | 1 | 84003149.9747 |  | -100%
| Final Design | 1 | 196062454.7302 |  | -100%
80.01 | Project Development |  |  | 52010036
80.02 | Engineering |  |  | 656711381
80.03 | Project Management for Design and Construction |  |  | 261659726
80.04 | Construction Adminsistration & Management |  |  | 206691401
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  |  | 39118681
80.08 | Start up |  |  | 20364663
Subtotal (80) |  |  | 280065604.7049 | 1236555888 | 341.5%
Subtotal (10-80) |  |  | 3648825938.0406 | 4531420839 | 24.19%
90 UNALLOCATED CONTINGENCY |  |  | 0 | 745176579
Subtotal (10-90) |  |  |  | 5276597418
100 FINANCE CHARGES |  |  | 0 | 473407227
| TOTAL COST OF ITEMS: |  | 3648825938.0406 | 5750004645 | 57.59%